

 Action Plan – 2026-2027
	Members: Year 5/6 Eco-Committee
Chair: ______________   Vice-chair: ______________   Secretary: ______________
Biodiversity champions: ______________________________________________
Adults who help us: Eco-Coordinator ____________, caretaker ____________

	Targets:
1. Set up our Eco-Committee and meet regularly, keeping minutes and telling our classes what we decide.
2. Check our school environment (all nine Eco-Schools topics) and look closely at the biodiversity in our grounds.
3. Apply for the Keep Wales Tidy Mini Garden Package (Mini Wildlife Garden). If we get it, build and look after our mini garden. If we don't, make our own wildlife area with bird feeders, bug hotels and wildflowers.
4. Get our evidence ready for our Green Flag award review in the autumn term.
5. Write a new Eco-Code about biodiversity and make sure the whole school knows it.
6. Count the wildlife in our grounds three times this year to see if our actions have helped.

	Action 
	Time Frame/Date
	Evaluation

	Autumn Term

	Vote for our chair, vice-chair and secretary. Meet every two weeks and tell our classes what we decide.
	September 2026
	

	Apply for the Keep Wales Tidy Mini Garden Package and choose a spot in our grounds for it (we need at least 5 square metres).
	September / October 2026
	

	Do the environmental review and walk around our grounds to find where minibeasts and birds live.
	October 2026
	

	Wildlife count 1: go on a minibeast hunt and do a bird watch. Record what we find.
	October 2026
	

	Put up bird feeders and take turns to keep them topped up.
	November 2026, then weekly
	

	Write our biodiversity Eco-Code and hold a whole-school vote.
	November 2026
	

	Get our Green Flag evidence ready and show the assessor our work.
	Autumn term 2026 (date to be confirmed)
	

	Spring Term

	Build bug hotels and a log pile for minibeasts.
	January / February 2027
	

	If we get the package: build our mini wildlife garden in a day with Keep Wales Tidy (raised beds, wildflowers, fruit shrubs and habitat boxes) and make a care rota.
	By the end of February 2027
	

	If we do not get the package: make our own wildlife area instead, for example by sowing wildflower seeds for bees and butterflies.
	March 2027
	

	Wildlife count 2: compare what we find with our autumn count.
	March 2027
	

	Lead an assembly to share our results and our Eco-Code.
	March 2027
	

	Summer Term

	Wildlife count 3: make graphs of all three counts. Have our actions helped?
	June 2027
	

	Check our Eco-Code and talk about what worked and what we would change.
	July 2027
	

	Plan who will look after the feeders and plants in the summer holidays, and hand over to next year's Eco-Committee.
	July 2027
	

	Next steps for 2027-2028:






